## AGILE - Product Backlog
Eric Weng and Jeffrey Kim | [5 empty] | For help use these links:
Racing Simulator | [5 empty] | https://www.mountaingoatsoftware.com/agile/scrum/product-backlog
Theme | I want to… | So that… | Notes | Priority | Status | http://www.mountaingoatsoftware.com/uploads/blog/smaller-product-backlog.jpg
Game | Create a video game based on racing | I can share it with my friends and peers and practice coding with Scratch. | Since a 3D racing game would be hard on Scratch, going for a 2D, possibly bird's eye view of track | High | Done
Game | Grab images and car sprites online | so that I can start working on creating the game | We found some good ones on google, can get started soon | High | Done
Game | Create code for car movement | I can add functionality to our game |  | High | Done
Game | Add a scoring system | I have a way to see how good players will be | Time and number of tries to calculate score? | High | Done
Game | Prevent users from just recrossing the finish line. | I can prevent cheaters and make the game more challenging |  | Medium | Done
Game | Add a menu screen | the game looks better | Menu will have to be plain as have limited time | Medium | Done
Game | Add a timer | users can try to beat thier own personal scores | Easy;timer variable exists in Scratch. PS: had to make own timer for more freedome | Medium | Done
Game | Instruction/Rules Slide | users can better understand game concept |  | Medium | Done
Game | Way to skip instructions | everytime you restart, its not a bother to read thru instructions again |  | Low | Done
Game | More Maps | users get more fun out of game | The game is already hard as is, so its pretty low priority to add another lovel | Low | WiP